## 工作表1
PROJECT SCHEDULE
Trip Recommender Application | Yuandi Tang & John Creighton
PROJECT DELIVERABLE | Travel Recommendation Application
START DATE | END DATE | OVERALL PROGRESS
2025-02-06 | 2025-04-08 | 100%
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Project Planning & API Research | Both | 2025-02-06 | 2025-08-06 | 7 | Finisheed | On Time
Database Design | John | 2025-09-06 | 06/15/2025 | 7 | Finisheed | On Time
API Integration | John | 06/16/2025 | 06/22/2025 | 7 | Finisheed | On Time
Data Storage & Modeling | Yuandi | 06/23/2025 | 06/29/2025 | 7 | Finisheed | On Time
Recommendation Logic Implementation | John | 06/30/2025 | 2025-06-07 | 7 | Finisheed | On Time
UI/UX Development | Yuandi | 2025-07-07 | 07/13/2025 | 7 | Finisheed | On Time
Integration and Testing | Both | 07/14/2025 | 07/20/2025 | 7 | Finisheed | On Time
Final Integration | Both | 07/21/2025 | 07/28/2025 | 7 | Finisheed | On Time
Final Report & Presentation | Both | 07/28/2025 | 2025-04-08 | 7 | Finisheed | On Time